## Sheet1
WOID	Status	Descriptions	ActionTaken	Request Date	Completion Date	Priority	Requester	AssignedTo	Location	Building	Area Type	Area Number	Equipment	Craft
14323	Work In Progress	Install detector in storage room - Storage rooms require detectors and main space / 2013 Ten-Year Health Life Safety Report		2/22/2017		High		Brewer, James L.	Dennis (12)			Teachers Lounge 001		Fire Alarm System
14328	Complete	Install exit signs at stair doors - East end of corridor required exit sign to stairs / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Brewer, James L.	Dennis (12)			Corridor 007		Electrical
14331	Complete	Install exit signs at stair doors - Bottom of stairs at exterior doors requires exit sign. / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Brewer, James L.	Dennis (12)			Stairwell 117, Stage 144		Electrical
14332	Complete	Install exit signs at stair doors - South end of corridor requires exit sign to corridor 231 / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Brewer, James L.	Dennis (12)			Corridor 219		Electrical
14333	Complete	Install additional emergency lights - Existing emergency lights not sufficient / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Wetzel, Michael T.	Dennis (12)			Stair 236, 013		Electrical
14337	Complete	Install detector in activity room - Top of stair shafts require fire detectors / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Brewer, James L.	Dennis (12)			Stairs 236, 228, 316, 307		Fire Alarm System
14338	Complete	Install emergency light in corridor at east end of stairwell. Exit corridor requires emergency light / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Wetzel, Michael T.	Dennis (12)			Corridor/Stair 136		Electrical
14341	Complete	Replace glazing - Glass not tempered safety glazing / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Shepherd, Duane	Dennis (12)			Social Worker 318 Door		Glass\Window Repairs
14344	Complete	Verify source of water. Provide repair to system. Cover exposed wood with aluminum - Head of curtain wall shows signs of rust. Wood is also exposed at roof edge / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Shepherd, Duane	Dennis (12)			Exterior Entry C		Windows
14345	Complete	Re-point masonry joints/remove & reseal control joints - Deteriorated/damaged masonry joint sealant at the perimeter of grills / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Burns, Cody	Dennis (12)			Exterior Masonry		Masonry
14347	Complete	Investigate source of damage and repair surface - Plaster wall is damaged due to water infiltration / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Woodrum, Jr., Glenn R.	Dennis (12)			Storage 004		Carpentry
14350	Complete	Remove asbestos containing floor tile. Install VCT - Asbestos containing floor tile is loose, friable, and causing a tripping hazard in vestibule. Stairway tiles are popping / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Hainline, Danny F.	Dennis (12)			Vestibule 001, Stair 136, 228		Flooring
14351	Complete	Verify source of water. Provide repair to system - Light fixtures have water stains. Roof or mechanical system leaking / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Woodrum, Jr., Glenn R.	Dennis (12)			Library 133		Roof
14352	Complete	Install missing tile - Ceiling tile missing / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Shepherd, Duane	Dennis (12)			Boyd 112		Ceiling Tile
14354	Complete	Repair/replace cracked or spalling masonry - Masonry wall has hole in exterior envelope / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Burns, Cody	Dennis (12)			Exterior Masonry		Masonry
14356	Complete	Investigate source of damage and repair surface - Wall near boiler room door is damaged due to water infiltration / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Woodrum, Jr., Glenn R.	Dennis (12)			Stair C		Carpentry
14359	Complete	Replace curtain wall system or replace sealant - Glazing sealant has deteriorated and is falling out. / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/12/2019	High		Shepherd, Duane	Dennis (12)			Exterior Window Exit C		Windows
14361	Complete	Replace urinals - Existing constant flush urinals are inefficient, health hazard, and worn out. / 2013 Ten-Year Health Life Safety Report	Serviced this unit, it is working properly.	2/22/2017	4/30/2018	High		Baity, James	Dennis (12)			Boys Toilets 134, 118		Plumbing
14340	Complete	Investigate source of damage and repair surface - Wall below window and above casework shows signs of water damage / 2013 Ten-Year Health Life Safety Report	Windows have been caulked.	2/22/2017	10/2/2017	High		Johnson, James S.	Dennis (12)			Classroom 301		Windows
14342	Complete	Investigate source of damage and repair surface - Ceiling in center of room appears to be wet. / 2013 Ten-Year Health Life Safety Report	Caulked the windows.	2/22/2017	10/2/2017	High		Johnson, James S.	Dennis (12)			Classroom 005, 141, 008		Ceiling Tile
14315	Complete	Classroom 305, 307, 309, 205, 208, 213 - Verify if glass in display cases are safety glazing. If not, replace with safety glass. Safety glazing label on display/bookcase is not readily visible. / 2013 Ten-Year Health Life Safety Report	All stamped tempered old castle.	2/22/2017	8/25/2017	High		Woodrum, Jr., Glenn R.	Dennis (12)			Various		Glass\Window Repairs
14343	Complete	Investigate cause of dripping, clean wall, and repair system - Walls at perimeter show signs of a liquid dripping down the wall. / 2013 Ten-Year Health Life Safety Report		2/22/2017	8/16/2017	High		Woodrum, Jr., Glenn R.	Dennis (12)			Corridor 219, 231		Carpentry
14313	Complete	Classroom 116, Corridor 121, Learning Center 104 - Remove obstruction - Location of boxes and furniture prevent required egress from space / 2013 Ten-Year Health Life Safety Report	Removed items	2/22/2017	5/3/2017	High		Herron, Scott	Dennis (12)			Various		Custodial
14346	Complete	Remove storage - Storage stacked in mechanical space / 2013 Ten-Year Health Life Safety Report	Removed items	2/22/2017	5/3/2017	High		Tapscott, Phil	Dennis (12)			Mechanical 011		Custodial
14335	Complete	Install pull stations adjacent to exterior doors - Pull stations required adjacent to exterior doors (in the natural path of escape from a fire) / 2013 Ten-Year Health Life Safety Report	Installed pullstation	2/22/2017	3/30/2017	High		Brewer, James L.	Dennis (12)			Vestibule 107, 132A, 001		Fire Alarm System
14329	Complete	Install pull stations adjacent to exterior doors - Pull stations required adjacent to exterior doors (in the natural path of escape from a fire) / 2013 Ten-Year Health Life Safety Report		2/22/2017	3/29/2017	High		Brewer, James L.	Dennis (12)			Stairwell 117, 106		Fire Alarm System
14353	Complete	Remove keyed lockset. Install lock/latch set self operable from inside of room - At door 302A, 309A, 310A, 313A, 314A, 315A, 207A, 208A, 209S, 212A, 215A - Door has thumb turn installed on door / 2013 Ten-Year Health Life Safety Report	Installed six deadbolt locks.	2/22/2017	3/20/2017	High		Karas, Paul J.	Dennis (12)			Classroom Doors		Doors and Hardware
14319	Complete	Doors 212A, 214A, 108A, 121B - Adjust door and hardware to re-align door within frame - Door does not close/out of alignment with frame. / 2013 Ten-Year Health Life Safety Report	Repaired doors and made adjustments.	2/22/2017	3/2/2017	High		Tennyson, Christopher	Dennis (12)			Various		Doors and Hardware
14321	Complete	Adjust door and hardware to align door within frame - Door does not close/out of alignment with frame / 2013 Ten-Year Health Life Safety Report	Made adjustment to door at room 207 and room 205.	2/22/2017	2/28/2017	High		Tennyson, Christopher	Dennis (12)			Stairs 207 and 205		Doors and Hardware
14322	Complete	Remove/discontinue use of manual door stop - Fire doors shall not be held open by door stops, wedges, and other unapproved hold-open devices. / 2013 Ten-Year Health Life Safety Report	Made adjustments to storage door at room 102.	2/22/2017	2/28/2017	High		Tennyson, Christopher	Dennis (12)			Storage 102		Doors and Hardware
14318	Complete	Removed/discontinue use of manual door stop. Fire doors shall not be held open by door stops, wedges, and other unapproved hold-open devices. / 2013 Ten-Year Health Life Safety Report	Removed manual door stops.	2/22/2017	2/27/2017	High		Tennyson, Christopher	Dennis (12)			Door 211A, 212A		Doors and Hardware
14320	Complete	Remove and install new door and frame or adjust existing to work within the same opening. Exterior door does not operate properly. The door sticks. Door position also allows gap below frame compromising the building envelope / 2013 Ten-Year Health Life Safety Report	Made adjustments to doors.	2/22/2017	2/27/2017	High		Tennyson, Christopher	Dennis (12)			Stair C/Exit G		Doors and Hardware
14349	Complete	Adjust door and hardware to re-align door within frame - Door does not close/out of alignment with frame / 2013 Ten-Year Health Life Safety Report	Made adjustments to doors in rooms 004, 008B, 235, and 142.	2/22/2017	2/27/2017	High		Tennyson, Christopher	Dennis (12)			Storage 235, 004, 142, 008B		Doors and Hardware
14389	Complete	Alarm box is loose. A ball hit the protective cover and caused the alarm to trigger.	Fixed pull station	2/22/2017	2/27/2017	Medium	Matthew J. Andrews	Durand, David	Dennis (12)		Cafeteria	gym		Fire Alarm System
14339	Complete	Install GFI outlet - Existing water cooler requires safety outlet / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/23/2017	High		Young, Robert A.	Dennis (12)			Corridor 126		Electrical
14357	Complete	Install bulb and lens in light fixture - Light fixture missing bulb and lens / 2013 Ten-Year Health Life Safety Report		2/22/2017	2/23/2017	High		Young, Robert A.	Dennis (12)			Storage 142, 004		Electrical
14294	Complete	Replaced glazing - Glazing is cracked at landing / 2013 Ten-Year Health Life Safety Report		2/21/2017	2/12/2019	High		Shepherd, Duane	Dennis (12)			Stair 316		Glass\Window Repairs
14301	Complete	Replace glazing - Glazing has cracked / 2013 Ten-Year Health Life Safety Report		2/21/2017	2/12/2019	High		Shepherd, Duane	Dennis (12)			Stairs 228		Glass\Window Repairs
14295	Complete	Verify if glass in classroom doors is safety glazing. If not, replace with safety glass. Safety glazing label is not readily visible on classroom doors and adjacent glazing / 2013 Ten-Year Health Life Safety Report	Replaced in rooms 138, 141, 230, & 234. Replaced confirmed plate glass in classroom doors.	2/21/2017	5/25/2017	High		Shepherd, Duane	Dennis (12)			Classrooms 005, 008, 141, 138, 234,230		Glass\Window Repairs
14299	Complete	Replace glazing - Glazing above door is cracked / 2013 Ten-Year Health Life Safety Report	Replaced and reglazed	2/21/2017	5/18/2017	High		Shepherd, Duane	Dennis (12)			Door 219B		Glass\Window Repairs
14293	Complete	Verify if glass in display case is safety glazing. If not, replace with safety glass. Safety glazing label on display/book case is not readily visible. / 2013 Ten-Year Health Life Safety Report	Each pane is clearly marked: Old Castle 2186 3304 Tempered 16 CFR 1201-1.11.	2/21/2017	5/9/2017	High		Shepherd, Duane	Dennis (12)			Classrooms 302, 301, 201, 212		Glass\Window Repairs
14297	Complete	Corridor 139, 007, 126, Mechanical 011, Classroom 005A - Adjust door and hardware to re-align door within frame. Door 139A does not close/out of alignment with frame / 2013 Ten-Year Health Life Safety Report	Made adjustments to doors.	2/21/2017	2/23/2017	High		Tennyson, Christopher	Dennis (12)			Corridor 139, 007,126, Mechanical 011, Classroom 0		Doors and Hardware
14298	Complete	Lock electrical panels - Electrical panel cover not locked/open during review / 2013 Ten-Year Health Life Safety Report	Denied ISBE - Maintenance not allowed using HLS funds / Completed using O&M - installed latches	2/21/2017	2/23/2017	High		Young, Robert A.	Dennis (12)			Corridor 231, 007		Electrical
14308	Complete	toilet located in the left hand stall (eastern most) in boys restroom across from cafeteria has leaking valve assembly	Replaced spud - vacuum breaker - spud trim & nut	2/21/2017	2/23/2017	Medium	Charles N. Loveall, Jr.	Alexander, Gary	Dennis (12)		Restroom (Boys)	across from cafeteria		Plumbing
14296	Complete	Remove/discontinue use of manual door stop - Fire doors shall not be held open by door stops, wedges, and other unapproved hold-open devices / 2013 Ten-Year Health Life Safety Report	Removed manual door stops in classrooms 234, 230, 141, 138, 005, 008.	2/21/2017	2/21/2017	High		Tennyson, Christopher	Dennis (12)			Classrooms 234, 230, 141, 138, 005, 008		Doors and Hardware